## Prioritized List
Nbr | Item | Strategic | Category | Areas Impacted | Level | Priority | Release | Prereq | Order | Status | Notes
1 | Validate nbr Rows/Cols are reasonable | n/a | QA | App | Detailed | High | 1.0.0 |  |  | Done
2 | Add overflow-x option to support horizontal scrolling | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done | Tables are allowed to expand to fit the columns if Horizontal Scroll is not selected. The overflow-x is set to "clip". Setting overflow-x to "hidden" would retain the table width, but the columns right of the table boundry would be inaccessible if the rows are not allowed to grow.
3 | Add Status to table state attributes | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
4 | Update receiveTable to set status = Saved | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
5 | Update createTable to set status = New | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
6 | Change deleteTable to change status = Deleted | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
7 | Create Persist function on editor "Update Post" | n/a | Infrastructure | App | Detailed | High | 1.0.0 |  |  | Done
8 | Create Persist action | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
9 | Create selector getDeletedTables | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
10 | From persist - delete Tables with status of Deleted | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
11 | From persist - deleteEntityRecort with status of Deleted | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
12 | From persist - status = New to Saved for table | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
13 | Delete table - REST | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
14 | Insert rows | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
15 | Delete rows | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
16 | Create status attribute in web service | n/a | Infrastructure | Rest | Detailed | Medium | 1.0.0 |  |  | Done
17 | Update createTableEntity to set status = New | n/a | Infrastructure | Rest, Store | Detailed | Medium | 1.0.0 |  |  | Done
18 | Update updateTableEntity add status | n/a | Infrastructure | Rest, Store | Detailed | Medium | 1.0.0 |  |  | Done
19 | Update receiveTableEntity to retrieve table Status | n/a | Infrastructure | Rest, Store | Detailed | Medium | 1.0.0 |  |  | Done
20 | Create optional grid border | n/a | Feature | App, Store | Detailed | High | 1.0.0 |  |  | Done
21 | Add "row" array/attributes to table object | n/a | Infrastructure | Database, Rest, Store | Medium | High | 1.0.0 |  |  | Done
22 | Insert columns | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
23 | Delete columns | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
24 | Add sort for select queries | n/a | Infrastructure | Database | Detailed | High | 1.0.0 |  |  | Done
25 | Update/PUT to database from block | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
26 | Optionally show/hide title | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
27 | Create/POST table in database from block | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
28 | Add attribute fields to database | n/a | Infrastructure | Database, Rest, Store | Medium | High | 1.0.0 |  |  | Done
29 | Add Table Name field to table creation page | n/a | Feature | App | Detailed | Medium | 1.0.0 |  |  | Done
30 | Delete table - On save when block removed | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
31 | Clean and document code | n/a | QA | App | Summary | High | 1.0.0 |  |  | Done
33 | Fix: Styling on BorderBox controls | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done | Opened Gutenberg issue (bug) #68772 on 1/19/2025. Team provided a workaround for the CSS. This is a temporary fix. Track progress of final solution through item 71.
34 | Remove console.log statements | n/a | QA | App | Summary | High | 1.0.0 |  |  | Done
37 | Banded rows | n/a | Feature | App | Summary | Low | 1.0.0 |  |  | Done
38 | Provide options on plugin uninstall | n/a | Infrastructure | App, Database | Medium | High | 1.0.0 |  |  | Done
40 | Refactor render.php for structural changes | n/a | Feature | App | Medium | High | 1.0.0 |  |  | Done
41 | Adjust Column width | n/a | Feature |  | Summary | Medium | 1.0.0 |  |  | Done
42 | Create optional grid lines border | n/a | Feature | App | Detailed | Medium | 1.0.0 |  |  | Done
44 | REST Service Performance | n/a | Infrastructure | Rest | Medium | High | 1.0.0 |  |  | Done | Performance is fine when testing on an full WP environment
45 | Make # Rows/Columns read only and update style | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
46 | Fix: Freeze Header Row makes header row hidden | n/a | Bug | App | Detailed | High | 1.0.0 |  |  | Done
47 | Remove the Site Save Message or make it meaningful | n/a | UX | App | Detailed | High | 1.0.0 |  |  | Done | Opened Gutenberg issue (bug) #68771 on 1/19/2025. Was able to update the entity so that the entity tile is displayed, but it still requires an additional confirmation and the ability to uncheck the entiy (Block) for save. This is bad user experience and even has the potential to have data appear to save, but not actually persist. There is a request to address the underlying "double confirmation" in issue #38714. Created issue 70 to track the Gutenberg teams response/update to this issue.
48 | Hide zoom link | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
49 | Stablize "new" table | n/a | QA | App | Medium | Medium | 1.0.0 |  |  | Done
50 | Implement web service security methods | n/a | Infrastructure | Rest | Detailed | Medium | 1.0.0 |  |  | Done
51 | Move Banded Row to Row level, not cell | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
57 | Add toggle to "enable" functionality | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
58 | Database build on plugin activation | n/a | Infrastructure | App, Database | Medium | High | 1.0.0 |  |  | Done
59 | Populate PostId in table | n/a | Infrastructure | App, Store, Database | Detailed | High | 1.0.0 |  |  | Done
60 | Adjust Row height | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
62 | update edit.js to remove depricated useSetting | n/a | QA | App | Detailed | High | 1.0.0 |  |  | Done
63 | Support multi-site | n/a | Infrastructure | App, Database | Summary | High | 1.0.0 |  |  | Done
66 | Gray "Freeze Header Row" when Headers are disabled | n/a | QA | App | Detailed | High | 1.0.0 |  |  | Done
67 | Remove red table border from block editor | n/a | UX | App | Detailed | High | 1.0.0 |  |  | Done
69 | Limit block width to the with of all grid columns | n/a | UX | App | Detailed | High | 1.0.0 |  |  | Done
76 | Deleting columns and/or rows is not working | n/a | Bug | Unknown | Detailed | High | 1.0.0 |  |  | Done
76 | Enable update permissions for Rest API | n/a | Security | Rest | Detailed | High | 1.0.0 |  |  | Done
82 | Table status is "undefined" when tables remounted after unmount | n/a | Bug | All | Detailed | Medium | 1.0.0 |  |  | Done
83 | Prevent deletion of header row | n/a | Bug | App | Detailed | Medium | 1.0.0 |  |  | Done | Removed "Delete" and "New" menu options if row is a header row
85 | Body Text alignment not implemented in frontend | n/a | Bug | UX | Detailed | High | 1.0.0 |  |  | Done
32 | Delete table - On deletion of post | n/a | Infrastructure | Rest, Store | Summary | Low | 1.1.0 |  |  | Done
54 | Delete table when post deleted from admin page | n/a | Infrastructure |  | Medium | Low | 1.1.0 |  |  | Done
61 | Create admin page to maintain tables | n/a | Feature |  | Summary | High | 1.1.0 |  |  | Done
87 | Create Cron to support maintenance to sync tables and posts | n/a | Feature | All | High |  | 1.1.0 |  |  | Done
89 | Create Separate Cell Component | No | Infrastructure | App | Medium |  | 1.1.1 |  | 20 | Done
74 | Export table (full object) | n/a | Feature | All | Summary |  | 1.1.1 |  |  | Done
91 | Enable keyboard navigation for table in editor | n/a | Feature | App | Low |  | 1.1.1 |  |  | Done
92 | Allow a TAB on the bottom right cell to insert a new row | n/a | Feature | App | Low |  | 1.1.1 |  |  | Done
68 | Replace "DropdownMenu" to "Menu" (currently experimental/locked) | No | UX | App | Detailed | Low | 1.2.0 |  |  | Done
78 | Create Data Types on Columns (e.g., text, image, link/button, number, etc.) | Yes | Feature | All | Summary | High | 1.2.0 |  |  | Done
93 | Add Date/Time column data type | Yes | Feature | App | Low | Medium | 1.2.0 |  |  | Done
94 | Allow for column names to be changed/updated | Yes | Feature | App | Low | Medium | 1.2.0 |  |  | Done
98 | Create navigation layer separate from editing | Yes | Feature | App | High |  | 1.2.0 |  |  | Done
99 | Empty date/time populates on front end as 1/1/1970 | No | Bug | App | Detailed | Urgent | 1.2.1 |  |  | Done | The error does not exist in development environment
96 | Arrow navigation doesn't always work on arrow key nav from edit mode | No | Bug | App | Detailed | High | 1.2.2 |  |  | Done
97 | Allow date/time to be edited by input as well as button | No | Feature | App | Detailed | Medium | 1.2.2 |  |  | Done | Time format don't match what is entered on the screen. Date and date/time appear okay
90 | Add ability to move rows, preferrably with drag and drop | Yes | Feature | App | Medium | High | 1.2.2 |  |  | Done
95 | Changing a date format causes error when editing existing value of different format | n/a | Bug | App | Detailed | High | 1.2.2 |  |  | Done
109 | Add ability to move columns, preferrably with drag and drop | Yes | Feature | UX | Detailed | High | 1.2.2 |  |  | Done
110 | Update insert row to allow both above and below current row | Yes | Feature | UX | Detailed | High | 1.2.2 |  |  | Done
111 | Update insert column to allow both left and right of current column | Yes | Feature | UX | Detailed | High | 1.2.2 |  |  | Done
125 | Update style on TextControl to be consistent with canvas rather than WP Admin | No | Bug | UX | Detailed | High | 1.2.2 |  |  | Done
124 | Fix grid lines so that double border lines don't appear | No | Bug | UX | Detailed | High | Roadmap |  | 5 | Roadmap
56 | Support undo/redo | Yes | Feature | App | High |  | Roadmap |  | 10 | Roadmap
73 | Export table (data only) as CSV | Yes | Feature | All | Summary | High | Roadmap |  | 10 | Roadmap
77 | Add support to dynamically load table data (e.g., posts, csv) | Yes | Feature | All | Summary |  | Roadmap | 78, 80 | 10 | Roadmap
101 | Provide Copy/Paste support between cells | Yes | Feature | App | High |  | Roadmap |  | 10 | Roadmap
104 | Show border on create table | Yes | Feature | UX | Detailed |  | Roadmap |  | 10 | Roadmap
105 | Update create table to input column names | No | Feature | App |  |  | Roadmap |  | 10 | Roadmap
118 | Support update of table status for Loaded | Yes | Feature | App | Detailed |  | Roadmap |  | 10 | Roadmap
119 | Update Create Table to attach an existing, Loaded table | Yes | Feature | App | Detailed |  | Roadmap |  | 10 | Roadmap
116 | Restore table from backup (JSON) | Yes | Feature | App |  |  | Roadmap |  | 15 | Roadmap
65 | Import table from CSV file (Simple) | Yes | Feature | App | Summary |  | Roadmap | 120, 121 | 20 | Roadmap
86 | Allow column names to be header row value | No | Feature | App | Summary |  | Roadmap |  | 20 | Roadmap
100 | Create data type registry | No | Infrastructure | App | High |  | Roadmap |  | 20 | Roadmap
83 | Provide option to select grid line color | No | Feature | App | Summary | Low | Roadmap |  | 30 | Roadmap
102 | Multi-cell select capability | Yes | Feature | App | High |  | Roadmap |  | 30 | Roadmap
112 | Mobile: Fix horizontal scrolling so that it work in mobile | No | Bug | UX | Detailed | High | Roadmap |  | 30 | Roadmap
113 | Mobile: Enable hide column capability | Yes | Feature | UX | High |  | Roadmap |  | 30 | Roadmap
114 | Mobile: Provide zoom view to see all columns for a row including hidden to drill | Yes | Feature | UX | High |  | Roadmap |  | 30 | Roadmap
115 | Mobile: Provide alternate view that shows each row as a card | Yes | Feature | UX | High |  | Roadmap |  | 30 | Roadmap
79 | Create frontend interactivity to sort, filter, etc. table data | Yes | Feature | All | Summary |  | Roadmap |  | 40 | Roadmap
117 | Import table from CSV file (Smart with data type support) | Yes | Feature | App | High |  | Roadmap | 120, 121 | 40 | Roadmap
122 | Support drag and drop to move rows up & down | No | UX | App | High | Medium | Roadmap |  | 40 | Roadmap
123 | Support drag and drop to move columns left & right | No | UX | App | High | Medium | Roadmap |  | 40 | Roadmap
26 | Allow Tab key to optionally create a new row from the bottom right cell | No | Feature | App | Medium | Medium | Roadmap |  | 50 | Roadmap
72 | Create complementary block to link a post containing details from a row in a table back to the post with the table | Yes | Feature | All | Summary |  | Roadmap |  | 50 | Roadmap
80 | Add subscription capability | Yes | Feature | All | Summary |  | Roadmap |  | 50 | Roadmap
103 | Multi-cell paste | Yes | Feature | App | High |  | Roadmap |  | 50 | Roadmap
108 | Create indexed search | Yes | Feature | App | Summary |  | Roadmap |  | 50 | Roadmap
120 | Refactor create table avoid render side-effcts | No | Infrastructure | App | Detailed |  | Roadmap |  | 50 | Roadmap
121 | Break out table Row as a component | No | Infrastructure | App | Detailed |  | Roadmap |  | 50 | Roadmap
106 | Add footer row and support aggregation | Yes | Feature | App | Summary |  | Roadmap |  | 60 | Roadmap
75 | Export all tables | No | Feature | All | Summary |  | Roadmap |  | 80 | Roadmap
84 | Provide front-end excel download capability | No | Feature | All | Summary |  | Roadmap |  | 80 | Roadmap
107 | Support socket.io feeds | No | Feature |  |  |  | Roadmap |  | 80 | Roadmap
35 | Determine if useEffect for # col/row is still needed | No | QA | App | Detailed | Medium | Roadmap |  | 99 | Roadmap | Deleting it broke the block. Have not looked at code alternatives
36 | Refactor rest services as controller class | No | Infrastructure | Rest | Detailed | Low | Roadmap |  | 99 | Roadmap
39 | Web service error returns | No | Infrastructure | Rest | Detailed | Medium | Roadmap |  | 99 | Roadmap
43 | Add Table creates a "get" 404 error | No | Bug | Rest | Detailed | Low | Roadmap |  | 99 | Roadmap
52 | Add nonce to web services | No | Infrastructure | Rest, Store | Detailed | Low | Roadmap |  | 99 | Roadmap | Nonces are handled automatically by Gutenberg and the Rest API for block editor. There will be a need when frontend editing is enabled.
53 | Sanitize arrays values (e.g., attributes fields) in web service PUTs | No | Infrastructure | Rest | Medium | High | Roadmap |  | 99 | Roadmap
55 | Job to remove orphan tables | No | Infrastructure |  | Summary | Low | Roadmap |  | 99 | Roadmap
70 | Remove the option to save specific table blocks after the save/publish post button has been pushed Refer to issue 47 | No | UX | App | Detailed | Low | Roadmap |  | 99 | Roadmap
71 | Track resolution to Gutenberg issue #68772 and remove workaround when final solution is in place. Reference item 33. | No | UX | App | Detailed | Low | Roadmap |  | 99 | Roadmap
81 | Investigate last (bottom right) cell dropping | No | Bug | TBD | Detailed | Medium | Roadmap |  | 99 | Roadmap | Appears new as of 4/23/25
88 | Maintenance: Log or delete post blocks without matching table | No | Feature | All | Medium | Medium | Roadmap |  | 99 | Roadmap
125 | Last Number Used

## Data Types
Impl Status | Priority | Verion |  | Outstanding | Data Type | Formats | Options | Adjustments To |  | Primary Component | Primary Render Tag
|  | Intro- duced | Last Update |  |  |  |  | Column Width | Style
Done |  | 1.0.0 | 1.2.0 | n/a | General | n/a | n/a | No | No | RichText | Div
In Process | High | 1.2.0 | 1.2.1 | Column Width, all Style | Date/Time | - Date - Time - DateTime (datetime-local) | DefaultToToday | Yes | Align | TextControl | Time
None | High |  |  |  | Number
None | High |  |  |  | Image
None | High |  |  |  | Checkbox
None | Low |  |  |  | Rating
None | Low |  |  |  | Lookup (prompt value)
None | Medium |  |  |  | Link
None | Medium |  |  |  | Post
None | Medium |  |  |  | Related Content
None | Medium |  |  |  | Table

## Sheet2
Editor | Component | Editor | index
attribute of EditorInterface call
Editor | Component | Editor Interface | index | Run customSavePanel ¦¦ SavePublishPanels if not in preview
- Passes the 4 attributes into the call (close, is, set callback, dirty for SavePublishPanels
- customSavePanel passed as prop of EditorInterface (calling function)
Editor | Component | save-publish-panels | index | Controls open/close of save panel and opens it on save when needed
Identifies dirty entities editor store that are NOT the post in the editor
Editor | Component | entities-saved-states | index | Produces save/cancel buttons with prompt "Are you ready to save?"
Has function EntityTypeList
|  |  | entity-type-list | Produces list of items to save with a drop down header from entityLabel (i.e., Table from the Dynamic Tables entity config).
Has function EntityTypeRecord
|  |  | entity-record-item | Produces the list items to be saved
All from the entity type in the type list
Identifier is the title from "experimentalGetTemplateInfo" in the Editor Store (we show "untitled" on the save screen for Dynamic Tables)
- the "template" is the entity to be saved.
- I think an entity attribute of "title" would result in something more relevant than "Untitled"
- odd that it is tied to the template and not the entity
- only retrieves dirty entity records where entity "kind" !== postType and "name" !== wp_template
+ our name = table, kind = dynamic-tables/v1