## Sheet1
Nbr | Item | Category | Areas Impacted | Level | Priority | Release | Prereq | Order | Status | Notes
14 | Create status attribute in web service | Infrastructure | Rest | Detailed | Medium | 1 |  |  | Done
15 | Update createTableEntity to set status = New | Infrastructure | Rest, Store | Detailed | Medium | 1 |  |  | Done
16 | Update updateTableEntity add status | Infrastructure | Rest, Store | Detailed | Medium | 1 |  |  | Done
17 | Update receiveTableEntity to retrieve table Status | Infrastructure | Rest, Store | Detailed | Medium | 1 |  |  | Done
51 | Populate PostId in table | Infrastructure | App, Store, Database | Detailed | High | 1 |  |  | Done
49 | Stablize "new" table | QA | App | Medium | High | 1 | 17 | 1 | Testing
32 | Add nonce to web services | Infrastructure | Rest, Store | Detailed | Medium | 1 |  | 2 | Open
33 | Implement web service security methods | Infrastructure | Rest | Detailed | Medium | 1 |  | 3 | Open
34 | Web service error returns | Infrastructure | Rest | Detailed | Medium | 1 |  | 4 | Open
50 | REST Service Performance | Infrastructure | Rest | Medium | High | 1 | 32 | 5 | Open
35 | Add Table creates a "get" 404 error | Bug | Rest | Detailed | Low | 1 |  | 6 | Open
41 | Hide zoom link | Feature | App | Detailed | High | 1 |  | 7 | Open
42 | Move Banded Row to Row level, not cell | Feature | App | Detailed | High | 1 |  | 8 | Open
46 | Fix styling on BorderBox controls | Feature | App | Detailed | High | 1 |  | 9 | Open
47 | Make # Rows/Columns read only and update style | Feature | App | Detailed | High | 1 |  | 10 | Open
58 | Remove red table border from block editor | UX | App | Detailed | High | 1 |  | 11 | Open
59 | Gray "Freeze Header Row" when Headers are disabled | QA | App | Detailed | High | 1 |  | 12 | Open
48 | Add toggle to "enable" functionality | Feature | App | Detailed | High | 1 |  | 13 | Open
36 | Sanitize arrays values (e.g., attributes fields) in web service PUTs | Infrastructure | Rest | Medium | High | 1 |  | 14 | Open
43 | Refactor render.php for structural changes | Feature | App | Medium | High | 1 |  | 15 | Open
56 | Determine if useEffect for # col/row is still needed | QA | App | Detailed | High | 1 |  | 16 | Open
57 | update edit.js to remove depricated useSetting | QA | App | Detailed | High | 1 |  | 17 | Open
60 | Remove the Site Save Message or make it meaningful | UX | App | Detailed | High | 1 |  | 18 | Open
1 | Add Status to table state attributes | Infrastructure | Store | Detailed | High | 1 |  |  | Done
2 | Update receiveTable to set status = Saved | Infrastructure | Store | Detailed | High | 1 |  |  | Done
3 | Update createTable to set status = New | Infrastructure | Store | Detailed | High | 1 |  |  | Done
4 | Change deleteTable to change status = Deleted | Infrastructure | Store | Detailed | High | 1 |  |  | Done
5 | Create Persist function on editor "Update Post" | Infrastructure | App | Detailed | High | 1 |  |  | Done
6 | Create Persist action | Infrastructure | Store | Detailed | High | 1 |  |  | Done
7 | Create selector getDeletedTables | Infrastructure | Store | Detailed | High | 1 |  |  | Done
8 | From persist - delete Tables with status of Deleted | Infrastructure | Store | Detailed | High | 1 |  |  | Done
9 | From persist - deleteEntityRecort with status of Deleted | Infrastructure | Store | Detailed | High | 1 |  |  | Done
10 | From persist - status = New to Saved for table | Infrastructure | Store | Detailed | High | 1 |  |  | Done
11 | Delete table - REST | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
12 | Insert rows | Feature | App, Store | Summary | High | 1 |  |  | Done
13 | Delete rows | Feature | App, Store | Summary | High | 1 |  |  | Done
18 | Create optional grid border | Feature | App, Store | Detailed | High | 1 |  |  | Done
19 | Add "row" array/attributes to table object | Infrastructure | Database, Rest, Store | Medium | High | 1 |  |  | Done
20 | Insert columns | Feature | App, Store | Summary | High | 1 |  |  | Done
21 | Delete columns | Feature | App, Store | Summary | High | 1 |  |  | Done
22 | Add sort for select queries | Infrastructure | Database | Detailed | High | 1 |  |  | Done
23 | Update/PUT to database from block | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
24 | Create/POST table in database from block | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
25 | Add attribute fields to database | Infrastructure | Database, Rest, Store | Medium | High | 1 |  |  | Done
27 | Delete table - On save when block removed | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
28 | Banded rows | Feature | App | Summary | Low | 1 |  |  | Done
30 | Adjust Column width | Feature |  | Summary | Medium | 1 |  |  | Done
37 | Create optional grid lines border | Feature | App | Detailed | Medium | 1 |  |  | Done
38 | Support multi-site | Infrastructure | App, Database | Summary | High | 1 | 14, 49 | 19 | Open
39 | Database build on plugin activation | Infrastructure | App, Database | Medium | High | 1 |  | 20 | Open
40 | Provide options on plugin deactivation | Infrastructure | App, Database | Medium | High | 1 |  | 21 | Open
44 | Remove document code | QA | App | Summary | High | 1 |  | 22 | Open
45 | Remove console.log statements | QA | App | Summary | High | 1 |  | 23 | Open
26 | Delete table - On deletion of post | Infrastructure | Rest, Store | Summary | Low | 1.1 |  |  | Open
29 | Refactor rest services as controller class | Infrastructure | Rest | Detailed | Low | 1.1 |  |  | Open
31 | Adjust Row height | Feature | App, Store | Summary | Low | 1.1 |  |  | Open
54 | Create admin page to maintain tables | Feature |  | Summary | Low | 1.1 |  |  | Open
55 | Create table from CSV file | Feature |  | Summary | Low | 1.1 |  |  | Open
61 | Enable undo functionality | Feature | App | Summary | Medium | 1.1 |  |  | Open
52 | Delete table when post deleted from admin page | Infrastructure |  | Medium | Low |  |  |  | Open
53 | Job to remove orphan tables | Infrastructure |  | Summary | Low |  |  |  | Open