## Prioritized List
Nbr | Item | Strategic | Category | Areas Impacted | Level | Priority | Release | Prereq | Order | Status | Notes
1 | Validate nbr Rows/Cols are reasonable | n/a | QA | App | Detailed | High | 1.0.0 |  |  | Done
2 | Add overflow-x option to support horizontal scrolling | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done | Tables are allowed to expand to fit the columns if Horizontal Scroll is not selected. The overflow-x is set to "clip". Setting overflow-x to "hidden" would retain the table width, but the columns right of the table boundry would be inaccessible if the rows are not allowed to grow.
3 | Add Status to table state attributes | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
4 | Update receiveTable to set status = Saved | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
5 | Update createTable to set status = New | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
6 | Change deleteTable to change status = Deleted | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
7 | Create Persist function on editor "Update Post" | n/a | Infrastructure | App | Detailed | High | 1.0.0 |  |  | Done
8 | Create Persist action | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
9 | Create selector getDeletedTables | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
10 | From persist - delete Tables with status of Deleted | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
11 | From persist - deleteEntityRecort with status of Deleted | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
12 | From persist - status = New to Saved for table | n/a | Infrastructure | Store | Detailed | High | 1.0.0 |  |  | Done
13 | Delete table - REST | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
14 | Insert rows | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
15 | Delete rows | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
16 | Create status attribute in web service | n/a | Infrastructure | Rest | Detailed | Medium | 1.0.0 |  |  | Done
17 | Update createTableEntity to set status = New | n/a | Infrastructure | Rest, Store | Detailed | Medium | 1.0.0 |  |  | Done
18 | Update updateTableEntity add status | n/a | Infrastructure | Rest, Store | Detailed | Medium | 1.0.0 |  |  | Done
19 | Update receiveTableEntity to retrieve table Status | n/a | Infrastructure | Rest, Store | Detailed | Medium | 1.0.0 |  |  | Done
20 | Create optional grid border | n/a | Feature | App, Store | Detailed | High | 1.0.0 |  |  | Done
21 | Add "row" array/attributes to table object | n/a | Infrastructure | Database, Rest, Store | Medium | High | 1.0.0 |  |  | Done
22 | Insert columns | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
23 | Delete columns | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
24 | Add sort for select queries | n/a | Infrastructure | Database | Detailed | High | 1.0.0 |  |  | Done
25 | Update/PUT to database from block | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
26 | Optionally show/hide title | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
27 | Create/POST table in database from block | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
28 | Add attribute fields to database | n/a | Infrastructure | Database, Rest, Store | Medium | High | 1.0.0 |  |  | Done
29 | Add Table Name field to table creation page | n/a | Feature | App | Detailed | Medium | 1.0.0 |  |  | Done
30 | Delete table - On save when block removed | n/a | Infrastructure | Rest, Store | Summary | High | 1.0.0 |  |  | Done
31 | Clean and document code | n/a | QA | App | Summary | High | 1.0.0 |  |  | Done
33 | Fix: Styling on BorderBox controls | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done | Opened Gutenberg issue (bug) #68772 on 1/19/2025. Team provided a workaround for the CSS. This is a temporary fix. Track progress of final solution through item 71.
34 | Remove console.log statements | n/a | QA | App | Summary | High | 1.0.0 |  |  | Done
37 | Banded rows | n/a | Feature | App | Summary | Low | 1.0.0 |  |  | Done
38 | Provide options on plugin uninstall | n/a | Infrastructure | App, Database | Medium | High | 1.0.0 |  |  | Done
40 | Refactor render.php for structural changes | n/a | Feature | App | Medium | High | 1.0.0 |  |  | Done
41 | Adjust Column width | n/a | Feature |  | Summary | Medium | 1.0.0 |  |  | Done
42 | Create optional grid lines border | n/a | Feature | App | Detailed | Medium | 1.0.0 |  |  | Done
44 | REST Service Performance | n/a | Infrastructure | Rest | Medium | High | 1.0.0 |  |  | Done | Performance is fine when testing on an full WP environment
45 | Make # Rows/Columns read only and update style | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
46 | Fix: Freeze Header Row makes header row hidden | n/a | Bug | App | Detailed | High | 1.0.0 |  |  | Done
47 | Remove the Site Save Message or make it meaningful | n/a | Enhancement | UX | Detailed | High | 1.0.0 |  |  | Done | Opened Gutenberg issue (bug) #68771 on 1/19/2025. Was able to update the entity so that the entity tile is displayed, but it still requires an additional confirmation and the ability to uncheck the entiy (Block) for save. This is bad user experience and even has the potential to have data appear to save, but not actually persist. There is a request to address the underlying "double confirmation" in issue #38714. Created issue 70 to track the Gutenberg teams response/update to this issue.
48 | Hide zoom link | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
49 | Stablize "new" table | n/a | QA | App | Medium | Medium | 1.0.0 |  |  | Done
50 | Implement web service security methods | n/a | Infrastructure | Rest | Detailed | Medium | 1.0.0 |  |  | Done
51 | Move Banded Row to Row level, not cell | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
57 | Add toggle to "enable" functionality | n/a | Feature | App | Detailed | High | 1.0.0 |  |  | Done
58 | Database build on plugin activation | n/a | Infrastructure | App, Database | Medium | High | 1.0.0 |  |  | Done
59 | Populate PostId in table | n/a | Infrastructure | App, Store, Database | Detailed | High | 1.0.0 |  |  | Done
60 | Adjust Row height | n/a | Feature | App, Store | Summary | High | 1.0.0 |  |  | Done
62 | update edit.js to remove depricated useSetting | n/a | QA | App | Detailed | High | 1.0.0 |  |  | Done
63 | Support multi-site | n/a | Infrastructure | App, Database | Summary | High | 1.0.0 |  |  | Done
66 | Gray "Freeze Header Row" when Headers are disabled | n/a | QA | App | Detailed | High | 1.0.0 |  |  | Done
67 | Remove red table border from block editor | n/a | Cleanup | UX | Detailed | High | 1.0.0 |  |  | Done
69 | Limit block width to the with of all grid columns | n/a | Enhancement | UX | Detailed | High | 1.0.0 |  |  | Done
76 | Deleting columns and/or rows is not working | n/a | Bug | Unknown | Detailed | High | 1.0.0 |  |  | Done
76 | Enable update permissions for Rest API | n/a | Security | Rest | Detailed | High | 1.0.0 |  |  | Done
82 | Table status is "undefined" when tables remounted after unmount | n/a | Bug | All | Detailed | Medium | 1.0.0 |  |  | Done
83 | Prevent deletion of header row | n/a | Bug | App | Detailed | Medium | 1.0.0 |  |  | Done | Removed "Delete" and "New" menu options if row is a header row
85 | Body Text alignment not implemented in frontend | n/a | Bug | UX | Detailed | High | 1.0.0 |  |  | Done
32 | Delete table - On deletion of post | n/a | Infrastructure | Rest, Store | Summary | Low | 1.1.0 |  |  | Done
54 | Delete table when post deleted from admin page | n/a | Infrastructure |  | Medium | Low | 1.1.0 |  |  | Done
61 | Create admin page to maintain tables | n/a | Feature |  | Summary | High | 1.1.0 |  |  | Done
87 | Create Cron to support maintenance to sync tables and posts | n/a | Feature | All | High |  | 1.1.0 |  |  | Done
89 | Create Separate Cell Component | No | Infrastructure | App | Medium |  | 1.1.1 |  | 20 | Done
74 | Export table (full object) | n/a | Feature | All | Summary |  | 1.1.1 |  |  | Done
91 | Enable keyboard navigation for table in editor | n/a | Feature | App | Low |  | 1.1.1 |  |  | Done
92 | Allow a TAB on the bottom right cell to insert a new row | n/a | Feature | App | Low |  | 1.1.1 |  |  | Done
68 | Replace "DropdownMenu" to "Menu" (currently experimental/locked) | No | Enhancement | UX | Detailed | Low | 1.2.0 |  |  | Done
78 | Create Data Types on Columns (e.g., text, image, link/button, number, etc.) | Yes | Feature | All | Summary | High | 1.2.0 |  |  | Done
93 | Add Date/Time column data type | Yes | Feature | App | Low | Medium | 1.2.0 |  |  | Done
94 | Allow for column names to be changed/updated | Yes | Feature | App | Low | Medium | 1.2.0 |  |  | Done
98 | Create navigation layer separate from editing | Yes | Feature | App | High |  | 1.2.0 |  |  | Done
99 | Empty date/time populates on front end as 1/1/1970 | No | Bug | App | Detailed | Urgent | 1.2.1 |  |  | Done | The error does not exist in development environment
90 | Add ability to move rows, preferrably with drag and drop | Yes | Feature | App | Medium | High | 1.2.2 |  |  | Done
95 | Changing a date format causes error when editing existing value of different format | n/a | Bug | App | Detailed | High | 1.2.2 |  |  | Done
96 | Arrow navigation doesn't always work on arrow key nav from edit mode | No | Bug | App | Detailed | High | 1.2.2 |  |  | Done
97 | Allow date/time to be edited by input as well as button | No | Feature | App | Detailed | Medium | 1.2.2 |  |  | Done | Time format don't match what is entered on the screen. Date and date/time appear okay
109 | Add ability to move columns, preferrably with drag and drop | Yes | Feature | UX | Detailed | High | 1.2.2 |  |  | Done
110 | Update insert row to allow both above and below current row | Yes | Feature | UX | Detailed | High | 1.2.2 |  |  | Done
111 | Update insert column to allow both left and right of current column | Yes | Feature | UX | Detailed | High | 1.2.2 |  |  | Done
125 | Update style on TextControl to be consistent with canvas rather than WP Admin | No | Bug | UX | Detailed | High | 1.2.2 |  |  | Done
128 | Add keyboard shortcut to move rows/columns | Yes | Feature | App | Detailed | High | 1.2.3 |  |  | Done
129 | Add keyboard shortcut hints to row/column menus | Yes | Feature | UX | Detailed | High | 1.2.3 |  |  | Done
135 | General data type is not displayed or editable | No | Bug | App | Detailed | Urgent | 1.2.3 |  |  | Done
133 | Add support for basic numberic content type | Yes | Feature | App | High |  | 1.2.4 |  |  | Done
136 | Create CSS class controller | Yes | Infrastructure | UX | Summary | Medium | 1.2.4 |  |  | Done
134 | Add keyboard shortcut to insert/delete rows/columns | Yes | Feature | App | Detailed | High | 1.2.5 |  |  | Done
137 | Support Aria semantics for screen readers | No | Enhancement | Accessibility | Medium | High | 1.2.5 |  |  | Done
140 | Theme colors are not appearing as selection options for color selection | No | Bug | UX | Detailed | High | 1.2.5 |  |  | Done
141 | Add support for contentOnly mode | No | WP Release Update | UX | High | Urgent | 1.2.5 |  |  | Done | Support WP 7.0 breaking changes
35 | Determine if useEffect for # col/row is still needed | No | QA | App | Detailed | Medium | 1.3.0 |  |  | Done | Deleting it broke the block. Have not looked at code alternatives
39 | Web service error returns | No | Infrastructure | Rest | Detailed | Medium | 1.3.0 |  |  | Done
43 | Add Table creates a "get" 404 error | No | Bug | Rest | Detailed | Low | 1.3.0 |  |  | Done
81 | Investigate last (bottom right) cell dropping | No | Bug | TBD | Detailed | Medium | 1.3.0 |  |  | Done | Appears new as of 4/23/25
120 | Refactor create table avoid render side-effcts | No | Infrastructure | App | Detailed |  | 1.3.0 |  |  | Done
101 | Provide Copy/Paste support between cells | Yes | Feature | App | High |  | 1.3.1 |  |  | Done
126 | Add notices framework | Yes | Infrastructure | App | Detailed | High | 1.3.1 |  |  | Done
131 | Create Cell menu | Yes | Infrastructure | App | Medium | High | 1.3.1 |  |  | Done
65 | Import table from CSV file (Simple) | Yes | Feature | App | Summary |  | 1.4.0 |  |  | Done
119 | Update Create Table to attach an existing, Loaded table | Yes | Feature | App | Detailed |  | 1.4.0 |  |  | Done
138 | On Render, text color is same as banded row color | No | Bug | UX | Detailed | High | 1.4.0 |  |  | Done
144 | Enable endpoint to get multiple tables | Yes | Infrastructure | Rest | High |  | 1.4.0 |  |  | Done
145 | Create a summary table store | Yes | Infrastructure | Store |  |  | 1.4.0 |  |  | Done
118 | Support update of table status for Loaded | Yes | Feature | App | Detailed |  | 1.4.1 |  |  | Done
146 | Support delete of table for unattached tables | Yes | Feature | App | Detailed |  | 1.4.1 |  |  | Done
73 | Export table (data only) as CSV | Yes | Feature | All | Summary |  | 1.4.2 |  |  | Done
116 | Restore table from backup (JSON) | Yes | Feature | App | Detailed |  | 1.4.2 |  |  | Done
145 | Add Checkbox column data type | Yes | Feature | App | Low | Medium | 1.4.3 |  |  | Done
56 | Hook into undo/redo subscription | Yes | Feature | App | High |  | 1.4.4 |  |  | Done
104 | Show border on create table | Yes | Feature | UX | Detailed |  | 1.4.4 |  |  | Done
147 | Fix bug preventing selection of hiding checkbox when no data is present | No | Bug | UX | Detailed | High | 1.4.4 |  |  | Done
146 | Support undo/redo | Yes | Feature | App | High | High | 1.4.5 |  |  | Done
150 | Add advanced edit dialog for multi-part cell content values | Yes | Infrastructure | UX | Detailed | HIgh | 1.4.6 |  |  | Done
151 | Add link content type | Yes | Feature | UX | Medium | High | 1.4.6 |  |  | Done
149 | Prevent new tables (attached) from going into the undo queue | No | Bug | Front End | Detailed | High | 1.4.7 |  |  | Done
152 | Add formatting options to Table Name display or make it RichText | No | Enhancement | UX | Detailed | Medium | 1.4.7 |  |  | Done
154 | Allow a single column with a bullet (choose bullet or numbered list) | No | Feature | UX | Detailed | Medium | 1.4.7 |  |  | Done
158 | Allow fields to be concatenated for display purposes to form a single text string from the values in the columns. Optionally make it a bulleted or numbered list. | No | Feature | App | Detailed | Medium | 1.4.7 |  |  | Done | Elected to make it apply to all columns, concatinated. Essentially #154 will support both.
159 | Fix bug that causes tables to be deleted when they should not be. | No | Bug | All | Detailed | Urgent | 1.4.8 |  |  | Done
160 | Make green cell border that shows the current cell go away when the block loses focus | No | Enhancement | UX | Detailed | Medium | 1.4.8 |  |  | Done
105 | Update create table to input column names | No | Feature | App |  |  | 1.4.9 |  | 1 | In Process | Done except for styling
144 | Coerce content types for paste | Yes | Feature | All | Summary | High | 1.4.9 |  |  | Done | See Data Type Conversion tab
156 | Allow the enter key during edit to close edit mode | No | Enhancement | App | Detailed | Medium | 1.4.9 |  | 3 | Done
153 | Add column option to make input required and optionally show a "required" indicator. | No | Enhancement | UX | Detailed | Medium | 1.4.9 |  | 4 | Open
124 | Fix grid lines so that double border lines don't appear | No | Bug | UX | Detailed | High | 1.4.9 |  | 5 | Open
132 | Table heading not appearing on render | No | Bug | Front End | Detailed | Urgent | 1.4.9 |  | 6 | Open | In prod, Table header was to be displayed but wasn't rendered. Refreshed post in edit and "display header" was cleared. Re-applied the display and it worked. Perhaps there is an issue on initial save?
148 | Evaluate support for RTC syncConfig and determine if support can be safely added based on updates to WordPress. | No | UX | App | Detailed | High | 1.4.9 |  | 7 | Open | Monitor ticket #80722
159 | Coerce content types for column content type updates | Yes | Enhancement | UX | Detailed | High | Roadmap | 144 | 20 | Roadmap
77 | Add support to dynamically load table data (e.g., posts, csv) | Yes | Feature | All | Summary |  | Roadmap | 80 | 20 | Roadmap
86 | Allow column names to be header row value | No | Feature | App | Summary |  | Roadmap |  | 20 | Roadmap
100 | Create data type registry in PHP and sync to Gutenberg | No | Infrastructure | App | High |  | Roadmap |  | 20 | Roadmap
127 | Move date/time cell class into column.classes | Yes | Infrastructure | App | Detailed | Low | Roadmap |  | 20 | Roadmap | Explore React tool that WD uses for organization
143 | Clone/Duplicate table from Maintenance Page | No | Feature | All | Summary | Medium | Roadmap |  | 20 | Roadmap
83 | Provide option to select grid line color | No | Feature | App | Summary | Low | Roadmap |  | 30 | Roadmap
102 | Multi-cell select capability | Yes | Feature | App | High |  | Roadmap |  | 30 | Roadmap
112 | Mobile: Fix horizontal scrolling so that it work in mobile | No | Bug | UX | Detailed | High | Roadmap |  | 30 | Roadmap
113 | Mobile: Enable hide column capability | Yes | Feature | UX | High |  | Roadmap |  | 30 | Roadmap
114 | Mobile: Provide zoom view to see all columns for a row including hidden to drill | Yes | Feature | UX | High |  | Roadmap |  | 30 | Roadmap
115 | Mobile: Provide alternate view that shows each row as a card | Yes | Feature | UX | High |  | Roadmap |  | 30 | Roadmap
79 | Create frontend interactivity to sort, filter, etc. table data | Yes | Feature | All | Summary |  | Roadmap | 139 | 40 | Roadmap
117 | Import table from CSV file (Smart with data type support) | Yes | Feature | App | High |  | Roadmap | 120, 121 | 40 | Roadmap
122 | Support drag and drop to move rows up & down | No | Feature | UX | High | Medium | Roadmap |  | 40 | Roadmap
123 | Support drag and drop to move columns left & right | No | Feature | UX | High | Medium | Roadmap |  | 40 | Roadmap
26 | Allow Tab key to optionally create a new row from the bottom right cell | No | Feature | App | Medium | Medium | Roadmap |  | 50 | Roadmap
72 | Create complementary block to link a post containing details from a row in a table back to the post with the table | Yes | Feature | All | Summary |  | Roadmap |  | 50 | Roadmap
80 | Add subscription capability | Yes | Feature | All | Summary |  | Roadmap |  | 50 | Roadmap
103 | Multi-cell paste | Yes | Feature | App | High |  | Roadmap |  | 50 | Roadmap
108 | Create indexed search | Yes | Feature | App | Summary |  | Roadmap |  | 50 | Roadmap
121 | Break out table Row as a component | No | Infrastructure | App | Detailed |  | Roadmap |  | 50 | Roadmap
130 | Create data type dumb registry Gutenberg | Yes | Infrastructure | App | Medium | High | Roadmap |  | 50 | Roadmap | Will be replaced following creation/sync of php registry
143 | Provide Copy/Paste support from external clipboard sources | Yes | Feature | App | High |  | Roadmap | 126, 130, 131 | 50 | Roadmap
106 | Add footer row and support aggregation | Yes | Feature | App | Summary |  | Roadmap |  | 60 | Roadmap
75 | Export all tables | No | Feature | All | Summary |  | Roadmap |  | 80 | Roadmap
84 | Provide front-end excel download capability | No | Feature | All | Summary |  | Roadmap |  | 80 | Roadmap
107 | Support socket.io feeds | No | Feature | TBD |  |  | Roadmap |  | 80 | Roadmap
36 | Refactor rest services as controller class | No | Infrastructure | Rest | Detailed | Low | Roadmap |  | 99 | Roadmap
52 | Add nonce to web services | No | Infrastructure | Rest, Store | Detailed | Low | Roadmap |  | 99 | Roadmap | Nonces are handled automatically by Gutenberg and the Rest API for block editor. There will be a need when frontend editing is enabled.
53 | Sanitize arrays values (e.g., attributes fields) in web service PUTs | No | Infrastructure | Rest | Medium | High | Roadmap |  | 99 | Roadmap
55 | Job to remove orphan tables | No | Infrastructure | DB, Cron | Summary | Low | Roadmap |  | 99 | Roadmap
70 | Remove the option to save specific table blocks after the save/publish post button has been pushed Refer to issue 47 | No | Enhancement | UX | Detailed | Low | Roadmap |  | 99 | Roadmap
71 | Track resolution to Gutenberg issue #68772 and remove workaround when final solution is in place. Reference item 33. | No | Enhancement | UX | Detailed | Low | Roadmap |  | 99 | Roadmap
88 | Maintenance: Log or delete post blocks without matching table | No | Feature | All | Medium | Medium | Roadmap |  | 99 | Roadmap
139 | Add explicit header-to-cell association if needed | No | Enhancement | Accessibility | Medium | Low | Roadmap |  | 99 | Roadmap | Likely front-end only. Triggered by table complexity including sorting, filtering, etc.
142 | Strengthen ability to detect and remove tables when post is not saved | No | Infrastructure | DB | Detailed | Medium | Roadmap |  | 99 | Roadmap | These become orphan tables and Cron identifies them. This is to make block clean-up more robust so there is less liklihood the orphan table will exist in the first place.
155 | Support conversion of a typed fractions to a single fraction character where one exists (e.g., 1/2 goes to a single character rather than 3 characters). | No | Enhancement | UX | Detailed | Medium | Roadmap |  | 99 | Roadmap
157 | Support column specific formatting so that all values are say bold, italics, a different font size or color,etc.) | No | Feature | App | Detailed | Medium | Roadmap |  | 99 | Roadmap
160 | Last Number Used

## Features
Category | Feature | Status | Premium?
Table Types & Creation Methods
| New empty | Available
| Load from unattached table | Available
| Clone | Available
| Wordpress Patterns | Available
| Import CSV | Available |  | Creates unattached table available for loading to a block
| Import/Restore Backup | Available |  | Optionally restores table or creates fully
| Wordpress native content |  |  | Filtered list of posts, pages, custom post types, etc.
External Data Source/CSV File
External Data Source/API
Navigation & Layout
| Set Column Width Dynamically | Available
| Insert Column | Available
| Delete Column | Available
| Move Column Left/Right | Available
| Insert Row | Available
| Delete Row | Available
| Move Row Up/Down | Available
| Basic copy/paste one cell | Available |  | Paste limited to values within a column
| Enhanced copy/paste One Cell | Available |  | Support paste from external sources
| Multi-cell copy/paste | Available
| Undo/Redo | Available
| Automatic data type conversion | Roadmap |  | Allow attempt to paste or conversion of existing data to a differents date type (e.g., general date to a data column type where interpretation is possible)
Formatting
| Header Row | Available
| Sticky Header with vertical scrolling | Available
| Optional horizontal scroll | Available
| Banded Rows | Available
Column Content Types (Basic)
| General | Available |  | Free-form data with formatting
| Date/Time | Available |  | Date, Time, or Date/Time
| Number | Available |  | Decimal, Integer, Percent, Currency
| Checkbox | Available |  | Standard, Toggle, Icon, Freeform
| Link | Roadmap
| Image | Roadmap
| Rating | Roadmap
| Button | Roadmap
Column Content Types (Basic)
| Prompt/Lookup | Roadmap |  | Based on another table
Maintenance
| Export Backup (JSON) | Available
| Export CVS | Available

## Data Types
Impl Status | Priority |  | Verion |  | Outstanding | Data Type | Formats | Options | Adjustments To |  | Primary Component | Primary Render Tag
|  | Status | Intro- duced | Last Update |  |  |  |  | Column Width | Style
Done |  | Done | 1.0.0 | 1.2.0 | n/a | General | n/a | n/a | No | No | RichText | Div
In Process | High | Pending Outstanding | 1.2.0 | 1.2.1 | Column Width, all Style | Date/Time | - Date - Time - DateTime (datetime-local) | - DefaultToToday - Auto format column | Yes | Align | TextControl | Time
In Process | High | Pending Outstanding | 1.2.4 |  | - Add support for multi-currency - Add decimal alignment | Number | - Number (decimal) - integer - percent - currency | - Thousand Separator - Currency? - Bracket negative numbers - Display negative in red - Auto format column | Yes | Align | TextControl | Data
None | High |  |  |  |  | Image
None | High | Pending Outstanding | 1.4.3 | 1.4.3 | Column Width | Checkbox | - Standard - Toggle - Icon - Freeform | - DefaultToToday - Hide when content empty - Default empty to checked - Auto format column | Yes | No | TableCheckbox | Div (Input/ Button)
None | Medium |  | 1.4.6 |  |  | Link |  | - Open in new tab | No | No | a href
None | Low |  |  |  |  | Rating
None | Low |  |  |  |  | Lookup (prompt value)
None | Medium |  |  |  |  | Post
None | Medium |  |  |  |  | Related Content
None | Medium |  |  |  |  | Table
ChatGPT Proposed Value Shapes | [5 empty] | General | Content
[7 empty] | attributes.value | { "type": "richtext", "raw": "<p>Hello <strong>world</strong></p>" }
attributes.refs
attributes.indexText
[6 empty] | Link | Content
[7 empty] | attributes.value | { "type": "url", "href": "https://example.com", "label": "Docs" }
attributes.refs
attributes.indexText
[6 empty] | Media | Content
[7 empty] | attributes.value | { "type": "media", "id": 123, "mime": "image/jpeg", "size": "medium" }
[7 empty] | attributes.refs | { "type": "attachment", "id": 123 }
attributes.indexText
[6 empty] | Post | Content
[7 empty] | attributes.value | { "type": "post", "id": 456, "postType": "page" }
[7 empty] | attributes.refs | { "type": "post", "id": 456 }
attributes.indexText

## Data Type Conversion
Conversion Method
- Cooerce: Attemp Conversion and deliver an compatibility error if data cannot be coerced
- Incompatible: Data Types cannot be coerced. Deliver a compatibility error when coercing
FROM: Data Type => | General | Number | Date/Time | Checkbox | Link
TO: Data Type
General |  | Cooerce | Cooerce | Cooerce | Incompatible
Number | Cooerce |  | Incompatible | Incompatible | Incompatible
Date/Time | Cooerce | Incompatible |  | Incompatible | Incompatible
Checkbox | Cooerce | Incompatible | Incompatible |  | Incompatible
Link | Incompatible | Incompatible | Incompatible | Incompatible

## date-time Data Shape
Object Shape |  |  |  | Type | State Variable | Default Value | Valid | Comments
Column Type Definition:
attributes.columnDataType { |  |  |  |  | dataType
| type, |  |  |  | dataType.type | date-time | date-time
settings {
|  | format, |  |  | dataTypeFormat | date | date ¦ time ¦ datetime-local
|  | defaultToToday, |  |  | dateDefaultToToday | false
|  | formatOptions { |  |  |  |  | Any integer
|  |  | updateColumnStyle, |  | updateColumnStyle | true | true ¦ false
}
}
}
Cell Content Definition:

## Number Data Shape
Object Shape |  |  |  | Type | State Variable | Default Value | Valid | Comments
attributes.columnDataType { |  |  |  |  | dataType
| type, |  |  |  | dataType.type | number | number
settings {
|  | format, |  |  | dataTypeFormat | number | number ¦ integer ¦ percent ¦ currency
formatOptions {
|  |  | decimalPlaces, |  | decimalPlaces | 0 | Any integer
|  |  | showCurrencySymbol, |  | currency | false | true ¦ false
|  |  | thousandSeparator, |  | thousandSeparator | true | true ¦ false
|  |  | redNegative, |  | redNegative | false | true ¦ false
|  |  | bracketNegative, |  | thousandSeparator | false | true ¦ false
|  |  | updateColumnStyle, |  | updateColumnStyle | true | true ¦ false
}
}
}

## Checkbox Data Shape
Object Shape |  |  |  | Type | State Variable | Default Value | Valid | Comments
attributes.columnDataType { |  |  |  |  | dataType
| type, |  |  |  | dataType.type | number | number
settings {
|  | format, |  |  | dataTypeFormat | number | number ¦ integer ¦ percent ¦ currency
formatOptions {
|  |  | decimalPlaces, |  | decimalPlaces | 0 | Any integer
|  |  | showCurrencySymbol, |  | currency | false | true ¦ false
|  |  | thousandSeparator, |  | thousandSeparator | true | true ¦ false
|  |  | redNegative, |  | redNegative | false | true ¦ false
|  |  | bracketNegative, |  | thousandSeparator | false | true ¦ false
|  |  | updateColumnStyle, |  | updateColumnStyle | true | true ¦ false
}
}
}

## Link Data Shape
Object Shape |  |  |  |  | Type | State Variable | Default Value | Valid | Comments
Column Type Definition:
attributes.columnDataType { | [5 empty] | dataType
| type, |  |  |  |  | dataType.type | link | link
settings {
|  | format, |  |  |  | dataTypeFormat | text | text
formatOptions {
}
}
}
Cell Content Definition:
attributes.value {
canonical {
|  | url |  |  | url |  |  | any well formed url
|  | label |  |  | text |  |  | plain text
|  | newTab |  |  | boolean |  | false | true ¦ false | Open link in new tab
|  | button { | [6 empty] | Future feature
|  |  | style | [5 empty] | Future feature
|  |  | icon | [5 empty] | Future feature
}
|  | appendedIcon [ | [6 empty] | Future feature
{
|  |  |  | position |  |  |  |  | Future feature
|  |  |  | icon |  |  |  |  | Future feature
}
]
}
| refs [ | [7 empty] | n/a
{},
]
| meta{ | [7 empty] | n/a
}
| overrides { | [7 empty] | n/a
}
| indexText | [5 empty] | Label
}

## Sheet3
The schema contract I would adopt
Property | Meaning | Authoritative? | Safe to regenerate?
canonical | Type-specific user value | Yes | No
refs | External object dependencies | Usually derived from canonical | Yes
meta | Supplementary or resolved information | No | Yes
overrides | Explicit per-cell exceptions to column rules | Yes | No
indexText | Search projection | No | Yes
cell.content | Cached display-ready HTML | No | Yes
That gives each area a durable purpose and avoids overlap.
The key refinement is that canonical and overrides can both be authoritative, but in different domains:
canonical owns the value
overrides owns intentional exceptions to column policy

## Sheet2
Editor | Component | Editor | index
attribute of EditorInterface call
Editor | Component | Editor Interface | index | Run customSavePanel ¦¦ SavePublishPanels if not in preview
- Passes the 4 attributes into the call (close, is, set callback, dirty for SavePublishPanels
- customSavePanel passed as prop of EditorInterface (calling function)
Editor | Component | save-publish-panels | index | Controls open/close of save panel and opens it on save when needed
Identifies dirty entities editor store that are NOT the post in the editor
Editor | Component | entities-saved-states | index | Produces save/cancel buttons with prompt "Are you ready to save?"
Has function EntityTypeList
|  |  | entity-type-list | Produces list of items to save with a drop down header from entityLabel (i.e., Table from the Dynamic Tables entity config).
Has function EntityTypeRecord
|  |  | entity-record-item | Produces the list items to be saved
All from the entity type in the type list
Identifier is the title from "experimentalGetTemplateInfo" in the Editor Store (we show "untitled" on the save screen for Dynamic Tables)
- the "template" is the entity to be saved.
- I think an entity attribute of "title" would result in something more relevant than "Untitled"
- odd that it is tied to the template and not the entity
- only retrieves dirty entity records where entity "kind" !== postType and "name" !== wp_template
+ our name = table, kind = dynamic-tables/v1