## Sheet1
Item | Category | Areas Impacted | Level | Priority | Order | Status | Notes
Add Status to table state attributes | Infrastructure | Store | Detailed | High |  | Done
Update receiveTable to set status = Saved | Infrastructure | Store | Detailed | High |  | Done
Update createTable to set status = New | Infrastructure | Store | Detailed | High | 1 | Test
Change deleteTable to change status = Deleted | Infrastructure | Store | Detailed | High |  | Done
Create Persist function on editor "Update Post" | Infrastructure | App | Detailed | High | 2 | Test
Create Persist action | Infrastructure | Store | Detailed | High | 3 | Open
Create selector getDeletedTables | Infrastructure | Store | Detailed | High | 4 | Open
Create selector getNewTables | Infrastructure | Store | Detailed | High | 5 | Open
From persist - delete Tables with status of Deleted | Infrastructure | Store | Detailed | High | 6 | Open
From persist - deleteEntityRecort with status of Deleted | Infrastructure | Store | Detailed | High | 7 | Open
From persist - status = New to Saved for table | Infrastructure | Store | Detailed | High | 8 | Open
From persist - status = New to Saved for entityRecord | Infrastructure | Rest | Detailed | High | 9 | Open
Delete table - REST | Infrastructure | Rest, Store | Summary | High | 10 | In Process
Insert rows | Feature | App, Store | Summary | High | 11 | Open
Delete rows | Feature | App, Store | Summary | High | 12 | Open
Create status attribute in web service | Infrastructure | Rest | Detailed | Medium | 13 | Open
Update createTableEntity to set status = New | Infrastructure | Rest, Store | Detailed | Medium | 14 | Open
Update updateTableEntity add status | Infrastructure | Rest, Store | Detailed | Medium | 15 | Open
Update receiveTableEntity to retrieve table Status | Infrastructure | Rest, Store | Detailed | Medium | 16 | Open
Create optional grid border | Feature | App, Store | Detailed | High |  | Open
Add "row" array/attributes to table object | Infrastructure | Database, Rest, Store | Medium | High |  | Done
Insert columns | Feature | App, Store | Summary | High |  | Done
Delete columns | Feature | App, Store | Summary | High |  | Done
Add sort for select queries | Infrastructure | Database | Detailed | High |  | Done
Update/PUT to database from block | Infrastructure | Rest, Store | Summary | High |  | Done
Create/POST table in database from block | Infrastructure | Rest, Store | Summary | High |  | Done
Add attribute fields to database | Infrastructure | Database, Rest, Store | Medium | High |  | Done
Delete table - On deletion of post | Infrastructure | Rest, Store | Summary | High |  | Open
Delete table - On save when block removed | Infrastructure | Rest, Store | Summary | High |  | Open | Cannot identify when post is being deleted
Banded columns | Feature | App | Summary | Low |  | Open
Refactor rest services as controller class | Infrastructure | Rest | Detailed | Low |  | Open
Adjust Column width | Feature |  | Summary | Medium |  | Done
Adjust Row height | Feature | App, Store | Summary | Medium |  | Open
Add nonce to web services | Infrastructure | Rest, Store | Detailed | Medium |  | Open
Implement web service security methods | Infrastructure | Rest | Detailed | Medium |  | Open
Web service error returns | Infrastructure | Rest | Detailed | Medium |  | Open
Add Table creates a "get" 404 error | Bug | Rest | Detailed | Low |  | Open
Sanitize arrays values (e.g., attributes fields) in web service PUTs | Infrastructure | Rest | Detailed | Low |  | Open