## Sheet1
Nbr | Item | Category | Areas Impacted | Level | Priority | Release | Prereq | Order | Status | Notes
49 | Stablize "new" table | QA | App | Medium | High | 1 | 17 | 1 | Testing
47 | Remove the Site Save Message or make it meaningful | UX | App | Detailed | High | 1 |  |  | Done | Opened Gutenberg issue (bug) #68771 on 1/19/2025. Was able to update the entity so that the entity tile is displayed, but it still requires an additional confirmation and the ability to uncheck the entiy (Block) for save. This is bad user experience and even has the potential to have data appear to save, but not actually persist. There is a request to address the underlying "double confirmation" in issue #38714. Created issue 70 to track the Gutenberg teams response/update to this issue.
33 | Fix: Styling on BorderBox controls | Feature | App | Detailed | High | 1 |  |  | Done | Opened Gutenberg issue (bug) #68772 on 1/19/2025. Team provided a workaround for the CSS. This is a temporary fix. Track progress of final solution through item 71.
69 | Limit block width to the with of all grid columns | UX | App | Detailed | High | 1 |  |  | Done
60 | Adjust Row height | Feature | App, Store | Summary | High | 1 |  |  | Done
46 | Fix: Freeze Header Row makes header row hidden | Bug | App | Detailed | High | 1 |  |  | Done
63 | Support multi-site | Infrastructure | App, Database | Summary | High | 1 | 14, 49 | 2 | Open
67 | Remove red table border from block editor | UX | App | Detailed | High | 1 |  | 3 | Open
38 | Provide options on plugin uninstall | Infrastructure | App, Database | Medium | High | 1 |  | 4 | In Process
58 | Database build on plugin activation | Infrastructure | App, Database | Medium | High | 1 |  | 16 | Done
40 | Refactor render.php for structural changes | Feature | App | Medium | High | 1 |  | 10 | Open
39 | Web service error returns | Infrastructure | Rest | Detailed | Medium | 1 |  | 99 | Open
43 | Add Table creates a "get" 404 error | Bug | Rest | Detailed | Low | 1 |  | 99 | Open
34 | Remove document code | QA | App | Summary | High | 1 |  | 99 | Open
35 | Remove console.log statements | QA | App | Summary | High | 1 |  | 99 | Open
44 | REST Service Performance | Infrastructure | Rest | Medium | High | 1 |  | 99 | Open
45 | Make # Rows/Columns read only and update style | Feature | App | Detailed | High | 1 |  |  | Done
50 | Implement web service security methods | Infrastructure | Rest | Detailed | Medium | 1 |  |  | Done
1 | Validate nbr Rows/Cols are reasonable | QA | App | Detailed | High | 1 |  |  | Done
2 | Add overflow-x option to support horizontal scrolling | Feature | App | Detailed | High | 1 |  |  | Done | Tables are allowed to expand to fit the columns if Horizontal Scroll is not selected. The overflow-x is set to "clip". Setting overflow-x to "hidden" would retain the table width, but the columns right of the table boundry would be inaccessible if the rows are not allowed to grow.
3 | Add Status to table state attributes | Infrastructure | Store | Detailed | High | 1 |  |  | Done
4 | Update receiveTable to set status = Saved | Infrastructure | Store | Detailed | High | 1 |  |  | Done
5 | Update createTable to set status = New | Infrastructure | Store | Detailed | High | 1 |  |  | Done
6 | Change deleteTable to change status = Deleted | Infrastructure | Store | Detailed | High | 1 |  |  | Done
7 | Create Persist function on editor "Update Post" | Infrastructure | App | Detailed | High | 1 |  |  | Done
8 | Create Persist action | Infrastructure | Store | Detailed | High | 1 |  |  | Done
9 | Create selector getDeletedTables | Infrastructure | Store | Detailed | High | 1 |  |  | Done
10 | From persist - delete Tables with status of Deleted | Infrastructure | Store | Detailed | High | 1 |  |  | Done
11 | From persist - deleteEntityRecort with status of Deleted | Infrastructure | Store | Detailed | High | 1 |  |  | Done
12 | From persist - status = New to Saved for table | Infrastructure | Store | Detailed | High | 1 |  |  | Done
13 | Delete table - REST | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
14 | Insert rows | Feature | App, Store | Summary | High | 1 |  |  | Done
15 | Delete rows | Feature | App, Store | Summary | High | 1 |  |  | Done
16 | Create status attribute in web service | Infrastructure | Rest | Detailed | Medium | 1 |  |  | Done
17 | Update createTableEntity to set status = New | Infrastructure | Rest, Store | Detailed | Medium | 1 |  |  | Done
18 | Update updateTableEntity add status | Infrastructure | Rest, Store | Detailed | Medium | 1 |  |  | Done
19 | Update receiveTableEntity to retrieve table Status | Infrastructure | Rest, Store | Detailed | Medium | 1 |  |  | Done
20 | Create optional grid border | Feature | App, Store | Detailed | High | 1 |  |  | Done
21 | Add "row" array/attributes to table object | Infrastructure | Database, Rest, Store | Medium | High | 1 |  |  | Done
22 | Insert columns | Feature | App, Store | Summary | High | 1 |  |  | Done
23 | Delete columns | Feature | App, Store | Summary | High | 1 |  |  | Done
24 | Add sort for select queries | Infrastructure | Database | Detailed | High | 1 |  |  | Done
25 | Update/PUT to database from block | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
27 | Create/POST table in database from block | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
28 | Add attribute fields to database | Infrastructure | Database, Rest, Store | Medium | High | 1 |  |  | Done
30 | Delete table - On save when block removed | Infrastructure | Rest, Store | Summary | High | 1 |  |  | Done
37 | Banded rows | Feature | App | Summary | Low | 1 |  |  | Done
41 | Adjust Column width | Feature |  | Summary | Medium | 1 |  |  | Done
42 | Create optional grid lines border | Feature | App | Detailed | Medium | 1 |  |  | Done
48 | Hide zoom link | Feature | App | Detailed | High | 1 |  |  | Done
51 | Move Banded Row to Row level, not cell | Feature | App | Detailed | High | 1 |  |  | Done
57 | Add toggle to "enable" functionality | Feature | App | Detailed | High | 1 |  |  | Done
59 | Populate PostId in table | Infrastructure | App, Store, Database | Detailed | High | 1 |  |  | Done
62 | update edit.js to remove depricated useSetting | QA | App | Detailed | High | 1 |  |  | Done
66 | Gray "Freeze Header Row" when Headers are disabled | QA | App | Detailed | High | 1 |  |  | Done
26 | Optionally show/hide title | Feature | App | Detailed | High | 1 |  |  | Done
29 | Add Table Name field to table creation page | Feature | App | Detailed | Medium | 1 |  |  | Done
31 | Determine if useEffect for # col/row is still needed | QA | App | Detailed | High | 1 |  | 99 | Open | Deleting it broke the block. Have not looked at code alternatives
32 | Delete table - On deletion of post | Infrastructure | Rest, Store | Summary | Low | 1.1 |  |  | Open
36 | Refactor rest services as controller class | Infrastructure | Rest | Detailed | Low | 1.1 |  |  | Open
52 | Add nonce to web services | Infrastructure | Rest, Store | Detailed | Low | 1.1 |  |  | Open | Nonces are handled automatically by Gutenberg and the Rest API for block editor. There will be a need when frontend editing is enabled.
53 | Sanitize arrays values (e.g., attributes fields) in web service PUTs | Infrastructure | Rest | Medium | High | 1.1 |  |  | Open
54 | Delete table when post deleted from admin page | Infrastructure |  | Medium | Low | 1.1 |  |  | Open
55 | Job to remove orphan tables | Infrastructure |  | Summary | Low | 1.1 |  |  | Open
61 | Create admin page to maintain tables | Feature |  | Summary | Low | 1.1 |  |  | Open
65 | Create table from CSV file | Feature |  | Summary | Low | 1.1 |  |  | Open
56 | Enable undo functionality | Feature | App | Summary | Medium | 1.1 |  |  | Open
68 | Replace "DropdownMenu" to "Menu" (currently experimental/locked) | UX | App | Detailed | Medium | 1.1 |  |  | Open
70 | Remove the option to save specific table blocks after the save/publish post button has been pushed Refer to issue 47 | UX | App | Detailed | High | 1.1 |  |  | Open
71 | Track resolution to Gutenberg issue #68772 and remove workaround when final solution is in place. Reference item 33. | UX | App | Detailed | Low | 1.1 |  |  | Open
71 | Last Number Used

## Sheet2
Editor | Component | Editor | index
attribute of EditorInterface call
Editor | Component | Editor Interface | index | Run customSavePanel ¦¦ SavePublishPanels if not in preview
- Passes the 4 attributes into the call (close, is, set callback, dirty for SavePublishPanels
- customSavePanel passed as prop of EditorInterface (calling function)
Editor | Component | save-publish-panels | index | Controls open/close of save panel and opens it on save when needed
Identifies dirty entities editor store that are NOT the post in the editor
Editor | Component | entities-saved-states | index | Produces save/cancel buttons with prompt "Are you ready to save?"
Has function EntityTypeList
|  |  | entity-type-list | Produces list of items to save with a drop down header from entityLabel (i.e., Table from the Dynamic Tables entity config).
Has function EntityTypeRecord
|  |  | entity-record-item | Produces the list items to be saved
All from the entity type in the type list
Identifier is the title from "experimentalGetTemplateInfo" in the Editor Store (we show "untitled" on the save screen for Dynamic Tables)
- the "template" is the entity to be saved.
- I think an entity attribute of "title" would result in something more relevant than "Untitled"
- odd that it is tied to the template and not the entity
- only retrieves dirty entity records where entity "kind" !== postType and "name" !== wp_template
+ our name = table, kind = dynamic-tables/v1